## Sheet1
RiskId | ComplianceId | RiskTitle | Criticality | PossibleDamage | Category | RiskType | BusinessImpact | RiskDescription | RiskLikelihood | RiskImpact | RiskExposureRating | RiskPriority | RiskMitigation | CreatedAt | FrameworkId | RiskMultiplierX | RiskMultiplierY
1 | 1 | Data Breach Due to Inadequate Assessment | High | Financial losses, reputational damage, legal penalties | Operational | Residual | Disruption of operations, loss of customer trust, regulatory fines | Failure to conduct annual assessments may lead to unidentified vulnerabilities and potential data breaches. | 8 | 9 | 72 | High | {"1": "Regularly update security measures", "2": "Implement data encryption protocols", "3": "Enhance access controls"} | 2025-10-10 |  | 0.1 | 0.1
2 | 2 | Data Breach Due to Inadequate Change Assessment | Medium | Financial losses, reputational damage, legal penalties | IT | Residual | Disruption of operations, loss of customer trust, regulatory fines | Failure to assess systems after significant changes may introduce vulnerabilities and lead to data breaches. | 5 | 7 | 35 | Medium | {"1": "Implement robust change management processes", "2": "Conduct regular security audits", "3": "Provide ongoing security training"} | 2025-10-10 |  | 0.1 | 0.1
3 | 3 | Data Breach Due to Unremediated Vulnerabilities | High | Financial losses, reputational damage | Operational | Residual | Disruption of operations, loss of customer trust | Failure to remediate identified vulnerabilities within 30 days may lead to unauthorized access to cardholder data and subsequent data breaches. | 8 | 9 | 72 | High | {"1": "Establish clear remediation timelines", "2": "Implement automated patch management tools", "3": "Regularly monitor and update security protocols"} | 2025-10-10 |  | 0.1 | 0.1
4 | 4 | Non-compliance due to lack of documentation | High | Potential regulatory fines and reputational damage | Compliance | Residual | Financial penalties, legal repercussions | Failure to document assessment findings and remediation actions may lead to inaccurate compliance reporting, resulting in non-compliance penalties and reputational damage. | 7 | 9 | 63 | High | {"1": "Regular training on documentation procedures", "2": "Implement automated documentation tools", "3": "Conduct regular audits of documentation"} | 2025-10-10 |  | 0.1 | 0.1
5 | 5 | Data Breach Due to Lack of Encryption | High | Financial losses, reputational damage, legal consequences | Operational | Residual | Disruption of operations, loss of customer trust, regulatory fines | Unauthorized access to cardholder data due to lack of encryption measures, leading to data breaches and associated damages | 8 | 9 | 72 | High | {"1": "Implement encryption for all cardholder data", "2": "Regularly update encryption protocols", "3": "Conduct security audits"} | 2025-10-10 |  | 0.1 | 0.1
6 | 6 | Data Breach Risk | High | Loss of sensitive data, financial penalties, damage to reputation | Operational | Current | Financial losses, legal consequences, reputational damage | Potential data breach due to unaddressed vulnerabilities in systems handling cardholder data | 8 | 9 | 72 | High | {"1": "Regular security assessments and updates", "2": "Employee training on security protocols", "3": "Implementation of encryption technologies"} | 2025-10-10 |  | 0.1 | 0.1
7 | 7 | Data Breach Risk | High | Unauthorized access to payment data and potential data breaches. | Operational | Current | Loss of customer trust, financial penalties, legal consequences. | Risk of unauthorized access to payment data leading to data breaches and potential financial and reputational damage. | 8 | 9 | 72 | High | {"1": "Implementing encryption measures", "2": "Regularly monitoring access logs", "3": "Conducting periodic security audits"} | 2025-10-10 |  | 0.1 | 0.1
8 | 8 | Unauthorized Access Risk | High | Data breaches and loss of cardholder data | Operational | Residual | Impact on network security and data protection | Risk of unauthorized access to cardholder data due to inadequate firewall configurations | 7 | 9 | 63 | High | {"1": "Regularly review firewall configurations", "2": "Implement industry-standard configurations", "3": "Conduct penetration testing"} | 2025-10-10 |  | 0.1 | 0.1
9 | 9 | Firewall Rule Misconfiguration Risk | Medium | Security vulnerabilities due to misconfigured firewall rules | IT | Residual | Impact on network security and data protection | Risk of security vulnerabilities arising from misconfigured firewall rules and access controls | 6 | 7 | 42 | Medium | {"1": "Document all firewall rules and access controls", "2": "Regularly update and review documentation", "3": "Implement access control policies"} | 2025-10-10 |  | 0.1 | 0.1
10 | 10 | Unauthorized Access Risk | High | Unauthorized access to sensitive data and security breaches | IT | Residual | IT security and data protection | Failure to change default passwords may lead to unauthorized access to critical systems and data | 8 | 9 | 72 | High | {"1": "Implement multi-factor authentication for added security", "2": "Enforce regular password changes every 90 days", "3": "Implement account lockout policies after multiple failed login attempts"} | 2025-10-10 |  | 0.1 | 0.1
11 | 11 | Unauthorized Access to Cardholder Data | High | Data breaches, financial losses, reputational damage | IT | Current | Impact on data security and compliance with regulations | Risk of unauthorized individuals intercepting cardholder data during transmission | 8 | 9 | 72 | High | {"1": "Implement strong encryption algorithms like AES-256", "2": "Regularly review encryption methods", "3": "Monitor network traffic for anomalies"} | 2025-10-10 |  | 0.1 | 0.1
12 | 12 | Unauthorized Access to Stored Cardholder Data | High | Data breaches, financial losses, reputational damage | IT | Current | Impact on data security and compliance with regulations | Risk of unauthorized individuals gaining access to stored cardholder data | 8 | 9 | 75.96 | High | {"1": "Implement strong encryption algorithms like AES-256", "2": "Regularly review encryption methods", "3": "Implement access controls and monitoring"} | 2025-10-10 |  | 0.1 | 0.1
13 | 13 | Unauthorized Access to Cardholder Data | High | Data breaches, regulatory fines, reputational damage | Operational | Residual | Loss of customer trust, financial penalties, legal consequences | Unauthorized access to cardholder data can lead to data breaches, regulatory violations, and reputational damage. | 8 | 9 | 72 | High | {"1": "Regularly review and update access controls", "2": "Provide training on access control policies", "3": "Implement multi-factor authentication"} | 2025-10-10 |  | 0.1 | 0.1
14 | 14 | Undetected Unauthorized Access | Medium | Data breaches, compliance violations, financial penalties | Operational | Residual | Loss of customer trust, legal consequences, reputational damage | Failure to detect unauthorized access through access log auditing can lead to data breaches, compliance violations, and financial penalties. | 6 | 8 | 48 | Medium | {"1": "Implement automated log monitoring tools", "2": "Conduct regular training on access log auditing", "3": "Define clear audit procedures"} | 2025-10-10 |  | 0.1 | 0.1
15 | 15 | Malware Infection Risk | High | Data breaches, loss of sensitive information, and system downtime | IT | Residual | IT operations, data security, and regulatory compliance may be impacted. | Failure to implement and maintain anti-virus software may lead to malware infections, compromising system security and data integrity. | 8 | 9 | 72 | High | {"1": "Regular updates and patches for anti-virus software", "2": "Periodic system scans for malware detection", "3": "Employee training on recognizing and reporting suspicious activities"} | 2025-10-10 |  | 0.1 | 0.1
16 | 16 | Outdated Anti-virus Software Risk | Medium | Ineffective protection against new malware threats | IT | Residual | IT operations and data security may be compromised. | Failure to automate updates for anti-virus software may leave systems vulnerable to new malware threats, increasing the risk of security breaches and data loss. | 6 | 7 | 42 | Medium | {"1": "Regular monitoring of update processes", "2": "Testing updates in a controlled environment before deployment", "3": "Establishing backup and recovery procedures in case of update failures"} | 2025-10-10 |  | 0.1 | 0.1
17 | 17 | Exploitation of Security Vulnerabilities | High | Data breaches, unauthorized access, and compromised system integrity | IT | Inherent | Loss of sensitive data, financial losses, and damage to reputation | Failure to implement secure coding practices may result in the exploitation of vulnerabilities by malicious actors, leading to data breaches and compromised system security. | 7 | 9 | 63 | High | {"1": "Regular security training for development team members", "2": "Implementation of code review processes", "3": "Utilization of automated security testing tools"} | 2025-10-10 |  | 0.1 | 0.1
18 | 18 | Non-Compliance with Security Practices | Medium | Unauthorized access to cardholder data, non-compliance with regulations, financial penalties | IT | Inherent | Financial penalties, reputation damage, and non-compliance risks | Failure to integrate security practices into the development lifecycle may result in vulnerabilities in applications processing cardholder data, leading to non-compliance with regulations and financial penalties. | 6 | 7 | 42 | Medium | {"1": "Implement security checkpoints in the development lifecycle", "2": "Conduct security reviews after each release", "3": "Regularly update security practices based on industry standards"} | 2025-10-10 |  | 0.1 | 0.1
19 | 19 | Unauthorized Access to Cardholder Data | High | Data breaches, compliance violations | Operational | Residual | Loss of customer trust, financial penalties | Unauthorized access to cardholder data can result in data breaches and compliance violations, leading to financial and reputational damage. | 8 | 9 | 72 | High | {"1": "Regularly review and update access control lists", "2": "Implement multi-factor authentication for sensitive data access", "3": "Provide regular training on access control policies"} | 2025-10-10 |  | 0.1 | 0.1
20 | 20 | Unauthorized Access to Cardholder Data | High | Data breaches and financial losses | Operational | Residual | Loss of customer trust, financial penalties, legal consequences | Unauthorized access to cardholder data can result in data breaches, financial losses, and damage to the organization's reputation. | 8 | 9 | 72 | High | {"1": "Regularly review and update authentication mechanisms", "2": "Provide training to users on proper authentication practices", "3": "Implement continuous monitoring of authentication logs"} | 2025-10-10 |  | 0.1 | 0.1
21 | 21 | Unauthorized Access to Cardholder Data | High | Data breaches, financial losses, reputational damage | Operational | Residual | IT, Legal, Compliance | Unauthorized access to cardholder data can result in data breaches, financial losses, and reputational damage to the organization. | 8 | 9 | 72 | High | {"1": "Implement strong access controls and regular monitoring", "2": "Enforce least privilege access to cardholder data", "3": "Conduct regular security audits and penetration testing"} | 2025-10-10 |  | 0.1 | 0.1
22 | 22 | Data Breach Risk | High | Financial losses, reputational damage, legal consequences | Operational | Current | Potential loss of customer trust, regulatory fines, and legal actions | Failure to conduct quarterly security testing may lead to undetected vulnerabilities, increasing the risk of a data breach. | 7 | 9 | 63 | High | {"1": "Implement patches and updates promptly", "2": "Regularly review testing results for remediation", "3": "Enhance security controls based on testing findings"} | 2025-10-10 |  | 0.1 | 0.1
23 | 23 | Phishing Attack Risk | High | Financial loss, data exposure, reputational damage | Operational | Residual | Potential disruption of operations and loss of sensitive information | Employees may inadvertently disclose sensitive information in response to phishing emails, leading to security breaches. | 8 | 9 | 72 | High | {"1": "Implement email filtering and anti-phishing software", "2": "Conduct regular phishing simulation exercises", "3": "Educate employees on identifying phishing attempts"} | 2025-10-10 |  | 0.1 | 0.1
24 | 24 | Outdated Information Security Policy | High | Increased vulnerability to cyber threats and potential data breaches | Operational | Residual | Loss of sensitive data, financial losses, damage to reputation | Failure to update the information security policy annually may result in outdated security measures that are ineffective against evolving cyber threats. | 8 | 9 | 72 | High | {"1": "Regularly review and update the policy based on audit findings", "2": "Implement a feedback mechanism to gather input from stakeholders for policy updates", "3": "Provide regular training to ensure awareness of policy changes"} | 2025-10-10 |  | 0.1 | 0.1
25 | 25 | Non-Engagement of Qualified Security Assessor | High | Inaccurate compliance assessments and potential security vulnerabilities going unnoticed | Operational | Current | All business units may be impacted by non-compliance and security vulnerabilities. | Failure to engage a QSA may result in inaccurate compliance assessments, potentially leading to security breaches and non-compliance with regulatory requirements. | 7 | 9 | 63 | High | {"1": "Verify the QSA's PCI SSC approval status and relevant experience before engagement", "2": "Ensure assessments are scheduled at least 30 days in advance", "3": "Review assessment results within 14 days of completion"} | 2025-10-10 |  | 0.1 | 0.1
26 | 26 | Non-Compliance with SAQ Submission Deadline | High | Potential fines, reputational damage, and data breaches | Compliance | Current | Financial losses, legal consequences, and loss of customer trust | Failure to submit the SAQ on time may result in non-compliance with PCI DSS standards, leading to severe consequences. | 8 | 9 | 72 | High | {"1": "Establish clear SAQ submission deadlines", "2": "Implement automated reminders for deadline notifications", "3": "Conduct regular training on SAQ completion process"} | 2025-10-10 |  | 0.1 | 0.1
27 | 27 | Cyber Attacks Due to Undetected Vulnerabilities | High | Data breaches, financial losses, reputational damage | Operational | Residual | Disruption of operations, loss of customer trust | Failure to conduct quarterly vulnerability scans may lead to exploitation of vulnerabilities by threat actors, resulting in data breaches and financial losses. | 8 | 9 | 72 | High | {"1": "Engage ASV for quarterly scans", "2": "Review scan results promptly", "3": "Remediate identified vulnerabilities within 30 days"} | 2025-10-10 |  | 0.1 | 0.1
28 | 28 | Failure to Perform Quarterly Firewall Review | High | Unauthorized access to cardholder data, data breaches | Operational | Residual | Loss of sensitive data, financial penalties, damage to reputation | Failure to review firewalls quarterly may lead to vulnerabilities in network security and potential unauthorized access to cardholder data. | 7 | 9 | 63 | High | {"1": "Implement automated tools for firewall monitoring", "2": "Regular training for network security team", "3": "Strict access control policies"} | 2025-10-10 |  | 0.1 | 0.1
29 | 29 | Inadequate Firewall Rule Establishment | Medium | Data breaches, unauthorized access | Operational | Residual | Loss of sensitive data, regulatory fines | Failure to establish clear firewall rules may lead to misconfigurations, vulnerabilities, and potential unauthorized access to cardholder data. | 6 | 7 | 42 | Medium | {"1": "Regular review of firewall rules", "2": "Implement access control lists", "3": "Continuous monitoring of firewall logs"} | 2025-10-10 |  | 0.1 | 0.1
30 | 30 | Data Breach Risk | High | Financial loss, reputational damage | Operational | Residual | Loss of customer trust, regulatory fines | Failure to conduct quarterly vulnerability scans may lead to undetected security weaknesses and potential data breaches. | 8 | 9 | 72 | High | {"1": "Implement automated scanning tools", "2": "Regularly update scanning tools and methodologies", "3": "Train internal security teams on conducting scans"} | 2025-10-10 |  | 0.1 | 0.1
31 | 31 | Cyber Threat Exposure | High | Data breaches, regulatory fines | Operational | Residual | Loss of customer trust, financial penalties | Failure to conduct annual penetration testing may leave systems vulnerable to sophisticated cyber attacks. | 7 | 9 | 63 | High | {"1": "Engage third-party penetration testing firms", "2": "Implement continuous monitoring for suspicious activities", "3": "Regularly update penetration testing methodologies"} | 2025-10-10 |  | 0.1 | 0.1
32 | 32 | Data Breach Due to Lack of Encryption | High | Financial losses, reputational damage, regulatory fines. | IT | Residual | Loss of customer trust, legal consequences, financial penalties. | Failure to encrypt cardholder data may lead to unauthorized access, data breaches, and financial losses. | 8 | 9 | 72 | High | {"1": "Regularly review encryption effectiveness", "2": "Implement multi-factor authentication for access to encrypted data", "3": "Conduct regular security audits and penetration testing"} | 2025-10-10 |  | 0.1 | 0.1
33 | 33 | Unauthorized Access to Cardholder Data | High | Data breaches, financial losses, reputational damage | Operational | Inherent | Loss of customer trust, financial penalties, legal consequences | Unauthorized access to cardholder data can lead to data breaches, financial losses, and reputational damage for the organization | 8 | 9 | 72 | High | {"1": "Regularly review and update access controls", "2": "Implement multi-factor authentication for added security", "3": "Provide regular training to personnel on access control best practices"} | 2025-10-10 |  | 0.1 | 0.1
34 | 34 | Data Breach Risk | High | Financial losses, reputational damage | Operational | Current | Loss of customer trust, regulatory fines | Unauthorized access to cardholder data due to unaddressed vulnerabilities | 8 | 9 | 72 | High | {"1": "Implement multi-factor authentication", "2": "Encrypt sensitive data", "3": "Regularly review access controls"} | 2025-10-10 |  | 0.1 | 0.1
35 | 35 | Post-Change Vulnerability Risk | Medium | Data breaches, financial losses | Operational | Current | Disruption of services, loss of revenue | Exploitation of security weaknesses post system changes leading to unauthorized access | 6 | 8 | 48 | Medium | {"1": "Implement intrusion detection systems", "2": "Regularly review system logs", "3": "Conduct regular security audits"} | 2025-10-10 |  | 0.1 | 0.1
36 | 36 | Security Breach Due to Undetected Vulnerabilities | High | Exposure to security breaches and data theft. | Operational | Residual | IT Department | Failure to conduct quarterly vulnerability scans may lead to undetected vulnerabilities that could be exploited by attackers, resulting in a security breach. | 8 | 9 | 72 | High | {"1": "Implement patches and updates promptly", "2": "Implement network segmentation to limit exposure", "3": "Implement intrusion detection systems"} | 2025-10-10 |  | 0.1 | 0.1
37 | 37 | New Vulnerabilities Introduced by System Changes | Medium | Introduction of new vulnerabilities due to system changes. | Operational | Residual | IT Department | Failure to conduct vulnerability scans after major system updates may lead to the introduction of new vulnerabilities, potentially compromising system security. | 6 | 7 | 42 | Medium | {"1": "Conduct thorough testing after system updates", "2": "Implement change management processes", "3": "Monitor system behavior post-update"} | 2025-10-10 |  | 0.1 | 0.1
38 | 38 | Unauthorized Access to Payment Card Data | High | Data breaches, financial losses | Operational | Residual | Loss of customer trust, financial penalties | Failure to remediate vulnerabilities may result in unauthorized access to payment card data, leading to data breaches and financial losses. | 8 | 9 | 72 | High | {"1": "Implement security patches promptly", "2": "Regularly update security tools and software", "3": "Conduct regular vulnerability scans"} | 2025-10-10 |  | 0.1 | 0.1
39 | 39 | Unauthorized Access to Cardholder Data | High | Data breaches, financial loss, reputational damage | Operational | Current | Loss of customer trust, regulatory fines, legal actions | Unauthorized access to cardholder data can lead to data breaches and financial loss. | 8 | 9 | 72 | High | {"1": "Implement RBAC for access control", "2": "Regular access reviews and audits", "3": "Implement strong password policies"} | 2025-10-10 |  | 0.1 | 0.1
40 | 40 | Unauthorized Access to Cardholder Data | High | Data breaches, financial loss, reputational damage. | Operational | Current | Potential loss of sensitive data, financial penalties, damage to reputation. | Unauthorized access to cardholder data due to weak password policies could lead to data breaches and financial loss. | 8 | 9 | 72 | High | {"1": "Implement automated tools for enforcing password complexity and expiration policies", "2": "Provide regular training on password security best practices", "3": "Implement multi-factor authentication for added security"} | 2025-10-10 |  | 0.1 | 0.1
41 | 41 | Unauthorized Remote Access to Systems | Medium | Data breaches, financial loss, reputational damage. | Operational | Current | Potential unauthorized access to sensitive systems, financial loss, reputational damage. | Unauthorized remote access to systems handling cardholder data could lead to data breaches and financial loss. | 7 | 8 | 56 | Medium | {"1": "Implement multi-factor authentication for all remote access users", "2": "Regularly review and update remote access policies", "3": "Monitor remote access logs for suspicious activity"} | 2025-10-10 |  | 0.1 | 0.1
42 | 42 | Data Breach Risk | High | Financial losses, reputational damage | IT | Residual | Loss of customer trust, legal consequences | Failure to conduct quarterly vulnerability scans may lead to unidentified security weaknesses and potential data breaches. | 8 | 9 | 72 | High | {"1": "Implement regular vulnerability scanning schedule", "2": "Ensure timely remediation of identified vulnerabilities", "3": "Enhance network monitoring capabilities"} | 2025-10-10 |  | 0.1 | 0.1
43 | 43 | Network Change Vulnerability Risk | Medium | Unauthorized access, data breaches | IT | Residual | Disruption of operations, financial losses | Failure to conduct post-network change vulnerability scans may result in unidentified vulnerabilities and potential exploitation by malicious actors. | 6 | 8 | 48 | Medium | {"1": "Implement immediate post-change vulnerability scans", "2": "Enhance change management process for security reviews", "3": "Train IT staff on identifying post-change vulnerabilities"} | 2025-10-10 |  | 0.1 | 0.1
44 | 44 | Data Breach Risk | High | Data loss, legal penalties, reputational damage | IT | Current | Loss of customer trust, financial liabilities | Unauthorized access to cardholder data due to unaddressed vulnerabilities from lack of penetration testing | 8 | 9 | 72 | High | {"1": "Implement multi-factor authentication", "2": "Encrypt sensitive data at rest and in transit", "3": "Regularly review access controls"} | 2025-10-10 |  | 0.1 | 0.1
45 | 45 | Data Breach Due to Lack of Monitoring | High | Financial losses, reputational damage | Operational | Residual | Loss of customer trust, regulatory fines | Failure to monitor network traffic could lead to undetected security incidents and data breaches | 8 | 9 | 72 | High | {"1": "Implement continuous monitoring procedures", "2": "Regularly review SIEM alerts", "3": "Conduct regular security training"} | 2025-10-10 |  | 0.1 | 0.1
46 | 46 | Non-compliance with PCI DSS Training | High | Data breaches, financial penalties, reputational damage | Operational | Current | Potential financial losses, damage to reputation, legal consequences | Failure to complete PCI DSS training may result in employees mishandling cardholder data, leading to data breaches and non-compliance with regulatory requirements. | 7 | 9 | 63 | High | {"1": "Regular reminders and notifications to employees about upcoming training deadlines", "2": "Provide additional support and resources for employees who may struggle with the training content", "3": "Conduct periodic audits to ensure training completion"} | 2025-10-10 |  | 0.1 | 0.1
47 | 47 | Non-compliance with Annual Assessment Requirement | High | Potential fines and reputational damage | Compliance | Residual | Financial penalties, loss of customer trust | Failure to conduct annual assessments of compensating controls may lead to non-compliance with PCI DSS requirements, resulting in financial penalties and reputational damage. | 7 | 9 | 63 | High | {"1": "Implement automated reminders for annual assessments", "2": "Provide regular training to compliance team on assessment criteria", "3": "Conduct periodic audits to ensure compliance"} | 2025-10-10 |  | 0.1 | 0.1
48 | 48 | Inadequate Documentation and Storage of Assessment Results | Medium | Inability to demonstrate compliance during audits, potential fines | Compliance | Residual | Audit failures, financial penalties | Failure to properly document and store assessment results may result in the inability to demonstrate compliance with PCI DSS requirements during audits, leading to potential fines and audit failures. | 6 | 7 | 42 | Medium | {"1": "Implement secure document management system for storing assessment results", "2": "Regularly review and update access controls to ensure only relevant stakeholders have access to the documentation", "3": "Conduct periodic audits to verify documentation completeness"} | 2025-10-10 |  | 0.1 | 0.1
49 | 49 | Data Breach due to Inadequate Documentation | High | Financial losses, reputational damage, legal implications | Operational | Residual | Significant financial and reputational damage | Inadequate documentation of compensating controls may lead to security vulnerabilities and potential data breaches. | 8 | 9 | 72 | High | {"1": "Regular training on documentation procedures", "2": "Automated documentation tools implementation", "3": "Periodic audits of documentation accuracy"} | 2025-10-10 |  | 0.1 | 0.1
50 | 50 | Data Breach Risk | High | Financial losses, reputational damage, legal consequences | Operational | Residual | All business units involved in payment card processing | Unauthorized access to cardholder data due to incomplete or inaccurate self-assessment | 8 | 9 | 72 | High | {"1": "Regular training and awareness programs on PCI DSS requirements", "2": "Internal audits to verify compliance", "3": "Engagement of third-party assessors for independent validation"} | 2025-10-10 |  | 0.1 | 0.1
51 | 51 | Engagement of Unqualified QSA | High | Inaccurate PCI DSS assessments, data breaches, financial penalties | Compliance | Inherent | Payment processing departments may face non-compliance issues, data breaches, and financial losses. | Engaging an unqualified QSA may lead to inaccurate assessments, non-compliance with PCI DSS, and potential data breaches. | 8 | 9 | 72 | High | {"1": "Verify QSA credentials and experience", "2": "Conduct regular audits of QSA assessments", "3": "Provide ongoing training to QSAs"} | 2025-10-10 |  | 0.1 | 0.1
52 | 52 | Incorrect SAQ Selection Risk | High | Non-compliance with PCI DSS requirements, potential data breaches | Operational | Current | All business units handling payment card data | Incorrect selection of SAQ may lead to inadequate security measures and non-compliance with PCI DSS, increasing the risk of data breaches. | 7 | 9 | 63 | High | {"1": "Regular reviews of payment processing environment", "2": "Training for compliance team on SAQ selection criteria", "3": "Immediate review after significant changes"} | 2025-10-10 |  | 0.1 | 0.1
53 | 53 | Selection of Non-Compliant ASV | High | Unauthorized access to sensitive payment data, data breaches, and financial losses | Operational | Inherent | Potential financial losses, damage to reputation, and legal consequences | Selecting a non-compliant ASV increases the risk of security breaches and non-compliance with PCI DSS requirements, leading to severe consequences for the organization. | 8 | 9 | 72 | High | {"1": "Verify ASV compliance status before selection", "2": "Implement additional security measures to mitigate potential breaches", "3": "Regularly monitor ASV performance and compliance"} | 2025-10-10 |  | 0.1 | 0.1
54 | 54 | Unclear Engagement Terms with ASV | High | Misaligned expectations, missed deadlines, and potential security breaches | Operational | Inherent | Delays in vulnerability remediation, increased exposure to security threats | Failure to establish clear engagement terms with the ASV may result in delays, miscommunication, and compromised security posture. | 7 | 9 | 63 | High | {"1": "Regular contract reviews and updates", "2": "Ongoing communication with ASV to address any issues", "3": "Escalation process for unresolved contract disputes"} | 2025-10-10 |  | 0.1 | 0.1
55 | 55 | Delayed Vulnerability Scan Reporting | Medium | Unaddressed security vulnerabilities, potential data breaches | IT | Inherent | Increased exposure to security threats, potential data loss | Failure to receive timely vulnerability scan reports may result in delayed remediation efforts, leaving systems vulnerable to exploitation. | 6 | 7 | 42 | Medium | {"1": "Establish clear reporting timelines in SLA", "2": "Implement automated report generation and delivery processes", "3": "Regularly validate scan reports for accuracy"} | 2025-10-10 |  | 0.1 | 0.1
56 | 56 | Data Breach Due to Inadequate QSA Assessment | High | Financial losses, reputational damage, legal consequences | Operational | Residual | All business units handling payment card data | Inadequate QSA assessment may result in vulnerabilities going undetected, leading to a data breach | 8 | 9 | 72 | High | {"1": "Enhance QSA selection criteria to include thorough background checks", "2": "Implement regular security training for QSAs", "3": "Establish clear communication channels between organization and QSAs"} | 2025-10-10 |  | 0.1 | 0.1
57 | 57 | Data Breach Risk | High | Data exposure, financial losses, reputational damage | Operational | Current | Loss of customer trust, legal liabilities, financial penalties | Undetected vulnerabilities in Internet-facing systems can lead to unauthorized access and data breaches. | 8 | 9 | 72 | High | {"1": "Implement multi-factor authentication for sensitive systems", "2": "Regularly update security patches and configurations", "3": "Conduct regular security awareness training for employees"} | 2025-10-10 |  | 0.1 | 0.1
58 | 58 | Data Breach Due to Non-Compliance | High | Financial losses, legal liabilities, and reputational harm | Operational | Current | Disruption of operations, loss of customer trust, regulatory fines | Non-compliance with SAQ completion requirements may expose payment card data to unauthorized access, leading to a data breach. | 8 | 9 | 72 | High | {"1": "Implement encryption for sensitive data", "2": "Regular security testing and monitoring", "3": "Incident response plan for data breaches"} | 2025-10-10 |  | 0.1 | 0.1
59 | 59 | Security Vulnerabilities Post-Environment Changes | Medium | Increased risk of data breaches, non-compliance penalties, and operational disruptions | Operational | Current | Loss of customer trust, financial losses, regulatory fines | Failure to update SAQ after significant changes in the payment environment may introduce new vulnerabilities and weaken security controls. | 6 | 8 | 48 | Medium | {"1": "Regular security assessments post-change", "2": "Continuous monitoring of updated systems", "3": "Immediate remediation of identified vulnerabilities"} | 2025-10-10 |  | 0.1 | 0.1
60 | 60 | Lack of Qualified Assessor Oversight | High | Inaccurate compliance assessment and potential security vulnerabilities | Operational | Inherent | Potential security breaches and non-compliance | Failure to designate a qualified assessor may lead to inaccurate compliance assessment and security vulnerabilities. | 7 | 9 | 63 | High | {"1": "Verify qualifications and experience of the designated assessor", "2": "Provide training and resources to the assessor", "3": "Regularly review and monitor the assessor's performance"} | 2025-10-10 |  | 0.1 | 0.1
61 | 61 | Missed SAQ Deadline | Medium | Non-compliance and potential audit findings | Operational | Inherent | Potential audit findings and non-compliance | Failure to complete the SAQ within the deadline may result in non-compliance and audit findings. | 6 | 7 | 42 | Medium | {"1": "Establish clear communication channels for deadline reminders", "2": "Provide necessary resources for completion of SAQ", "3": "Implement a tracking system for monitoring completion"} | 2025-10-10 |  | 0.1 | 0.1
62 | 62 | Data Breach Due to Non-Compliance | High | Financial penalties, loss of customer trust, reputational damage | Operational | Residual | Loss of revenue, legal consequences, damage to brand reputation | Failure to engage a QSA may result in inadequate security assessments, leaving the organization vulnerable to data breaches and non-compliance fines. | 8 | 9 | 72 | High | {"1": "Regularly review and update security controls", "2": "Implement encryption for sensitive data", "3": "Conduct regular security awareness training"} | 2025-10-10 |  | 0.1 | 0.1
63 | 63 | Data Breach Due to Incomplete SAQ | High | Financial loss, reputational damage, legal consequences | Operational | Inherent | Disruption of operations, loss of customer trust | Incomplete SAQ may leave payment processing systems vulnerable to exploitation by malicious actors. | 8 | 9 | 72 | High | {"1": "Implement regular SAQ completion reminders", "2": "Provide training on SAQ completion best practices", "3": "Conduct periodic audits to verify SAQ completeness"} | 2025-10-10 |  | 0.1 | 0.1
64 | 64 | Penalties for Non-Submission of SAQ | Medium | Financial penalties, loss of credibility | Operational | Inherent | Financial burden, reputational damage | Failure to submit SAQ may result in non-compliance penalties and loss of trust from stakeholders. | 6 | 7 | 42 | Medium | {"1": "Establish clear submission process", "2": "Maintain records of submissions for audit trail", "3": "Implement controls for timely submission"} | 2025-10-10 |  | 0.1 | 0.1
65 | 65 | Data Breach Due to Non-compliance | High | Financial losses, reputational damage | Operational | Current | Loss of customer trust, regulatory fines | Failure to engage a QSA for annual assessments may result in vulnerabilities going undetected, leading to a potential data breach. | 8 | 9 | 72 | High | {"1": "Regularly review and act upon QSA recommendations for improvement", "2": "Implement necessary security measures based on assessment findings", "3": "Conduct regular security training for staff handling payment card data"} | 2025-10-10 |  | 0.1 | 0.1
66 | 66 | Non-compliance with SAQ Submission Deadline | High | Fines, reputational damage, and potential data breaches | Compliance | Residual | Financial losses, loss of customer trust, and regulatory penalties | Failure to submit the SAQ within the specified deadline may result in non-compliance with PCI DSS requirements, leading to severe consequences. | 8 | 9 | 72 | High | {"1": "Implement automated reminders for SAQ submission deadlines", "2": "Provide additional resources and support for departments struggling with SAQ completion", "3": "Conduct regular reviews of SAQ submission status"} | 2025-10-10 |  | 0.1 | 0.1
67 | 67 | Data Breach Risk | High | Financial loss, reputational damage, legal consequences | Operational | Residual | Finance, IT, Compliance | Failure to engage a qualified QSA may lead to inaccurate compliance assessments, increasing the risk of a data breach. | 7 | 9 | 63 | High | {"1": "Verify QSA credentials and expertise before engagement", "2": "Regularly review and monitor QSA performance and reports", "3": "Implement recommendations provided by the QSA"} | 2025-10-10 |  | 0.1 | 0.1
68 | 68 | Undetected Vulnerabilities from Lack of ASV Engagement | High | Failure to engage an ASV may result in undetected vulnerabilities leading to potential data breaches or cyber attacks | Operational | Inherent | All business units within the organization may be impacted by a potential data breach or cyber attack | Failure to engage an ASV may result in undetected vulnerabilities in the organization's Internet-facing environments, increasing the risk of data breaches or cyber attacks. | 7 | 9 | 63 | High | {"1": "Establish a formal process for engaging ASVs", "2": "Maintain a list of approved ASVs for selection", "3": "Regularly review and update ASV engagement process"} | 2025-10-10 |  | 0.1 | 0.1
69 | 69 | Non-Compliance Due to Lack of Documentation | Medium | Lack of documentation may result in non-compliance during audits or inability to track remediation progress | Compliance | Inherent | Information Security and Compliance departments may face penalties for non-compliance or inability to track remediation progress | Failure to maintain documentation of vulnerability scans and remediation efforts may result in non-compliance during audits or inability to track progress in addressing identified vulnerabilities. | 6 | 7 | 42 | Medium | {"1": "Implement a centralized documentation system for scans and remediation efforts", "2": "Regularly review and update documentation to ensure accuracy", "3": "Train staff on proper documentation procedures"} | 2025-10-10 |  | 0.1 | 0.1
70 | 70 | Non-compliance with Annual SAQ Completion | High | Fines, penalties, or loss of payment card processing privileges | Compliance | Residual | Financial and operational impact on the organization | Failure to comply with the annual SAQ completion requirement may lead to regulatory sanctions, financial losses, and reputational damage. | 7 | 9 | 63 | High | {"1": "Implement a reminder system for annual SAQ completion deadlines", "2": "Provide training on how to determine the correct SAQ type", "3": "Regularly review and update SAQ documentation retention policies"} | 2025-10-10 |  | 0.1 | 0.1
71 | 71 | Non-compliance with PCI DSS assessment requirements | High | Fines, reputational damage, data breaches | Compliance | Current | Financial losses, reputational damage, legal consequences | Failure to engage a QSA for PCI DSS assessment may result in inaccurate compliance status, increased vulnerability to cyber threats, and potential data breaches. | 8 | 9 | 72 | High | {"1": "Regularly review and update PCI DSS compliance procedures", "2": "Provide ongoing training to staff handling payment card data", "3": "Conduct regular internal audits to identify and address compliance gaps"} | 2025-10-10 |  | 0.1 | 0.1
72 | 72 | Undetected Vulnerabilities and Security Breaches | High | Security breaches, data loss, reputation damage | Operational | Current | Disruption of operations, financial losses, damage to reputation | Failure to conduct quarterly vulnerability scans may result in undetected vulnerabilities that could be exploited by malicious actors, leading to security breaches and potential data loss. | 8 | 9 | 72 | High | {"1": "Engage ASV for quarterly scans", "2": "Implement automated scanning tools for continuous monitoring", "3": "Establish immediate remediation process for critical vulnerabilities"} | 2025-10-10 |  | 0.1 | 0.1
73 | 73 | Non-compliance with Annual SAQ Completion | High | Potential data breaches and financial losses | Operational | Current | Disruption of payment processing operations and loss of customer trust | Failure to complete the SAQ annually may lead to non-compliance with PCI DSS standards, increasing the risk of data breaches and financial losses. | 7 | 9 | 63 | High | {"1": "Set up automated reminders for SAQ completion deadlines", "2": "Provide training on SAQ completion process", "3": "Implement regular audits of SAQ completion"} | 2025-10-10 |  | 0.1 | 0.1
74 | 74 | Data Breach Risk | High | Data exposure, financial losses, reputational damage | Compliance | Residual | All business units processing payment card transactions | Inadequate assessments by unqualified assessors may lead to vulnerabilities and potential data breaches | 8 | 9 | 72 | High | {"1": "Regularly review and update QSA selection criteria", "2": "Ensure timely engagement of QSAs for assessments", "3": "Implement recommendations from ROC"} | 2025-10-10 |  | 0.1 | 0.1
75 | 75 | Undetected Vulnerabilities from Infrequent Scans | High | Data breaches, financial losses, reputational damage | Operational | Inherent | Disruption of operations, loss of customer trust, regulatory fines | Failure to conduct quarterly scans may result in undetected vulnerabilities that could be exploited by malicious actors, leading to data breaches and financial losses. | 8 | 9 | 72 | High | {"1": "Engage an approved ASV for quarterly scans", "2": "Implement timely remediation of identified vulnerabilities", "3": "Regularly monitor and update security measures"} | 2025-10-10 |  | 0.1 | 0.1
76 | 76 | Incorrect SAQ Type Determination | Medium | Potential non-compliance penalties and reputational damage | Operational | Inherent | Financial losses, regulatory fines, damage to reputation | Incorrectly determining SAQ type may result in misalignment with actual compliance requirements, leading to non-compliance consequences. | 6 | 8 | 48 | Medium | {"1": "Provide training to staff on SAQ type determination process", "2": "Implement regular review processes for SAQ type determination accuracy", "3": "Engage third-party experts for validation of SAQ type determination"} | 2025-10-10 |  | 0.1 | 0.1
77 | 77 | Late or Inaccurate SAQ Submission | High | Non-compliance penalties, financial losses, reputational damage | Operational | Inherent | Financial losses, regulatory fines, damage to reputation | Delayed or inaccurate submission of SAQ may result in compliance violations, leading to penalties and reputational harm. | 7 | 9 | 63 | High | {"1": "Establish clear submission deadlines and processes", "2": "Implement regular reminders and follow-ups for SAQ completion and submission", "3": "Conduct internal audits to verify compliance with SAQ submission requirements"} | 2025-10-10 |  | 0.1 | 0.1